## Production Backlog Form
Production Task Chart
Production Infromation |  |  |  |  | Feature List
Production Name: |  | Down to Earth (DTE) |  |  | Sprint #1
Primary Maintainer: |  | Salvatore Calderone |  |  | Priority | Feature ID | Status | Feature | Notes | Branch
Secondary Maintainer: |  | Bobby Kemp |  |  | 1 | DTE-PRM-001 | CP | Character Class Design | Design class structure for Character class | Master
Team Information |  |  |  |  | 2 | DTE-PRM-002 | CP | NPC Class Design | Design class structure for NPCs (Non-Hostile) | Master
Division: |  | Programming |  |  | 3 | DTE-PRM-003 | CP | Enemy Class Design | Design class structure for Enemies | Master
Team Lead: |  | Charlie Shin |  |  | 4 | DTE-PRM-004 | CP | Player Class Design | Design class structure for Player | Master
Primary Maintainer: |  | Charlie Shin |  |  | 5 | DTE-PRM-005 | CP | Character Class Implement | Create Character Class script | DTE-PRM-005
Secondary Maintainer: |  | Bobby Kemp |  |  | 6 | DTE-PRM-006 | IW | Player Class Implement | Create Basic Player Class script | DTE-PRM-006
Team Members |  |  |  |  | 7 | DTE-PRM-007 | IW | Enemy Class Implement | Create Basic Enemy Class script | DTE-PRM-007
| Last Name | First Name | Initial | Position | 8 | DTE-PRM-008 | IW | NPC Class Implement | Create Basic NPC Class script | DTE-PRM-008
1 | Shin | Charlie | CS | Team Lead | 9 | DTE-PRM-009 | CP | Item Class Design | Design class structure for Item class | Master
2 | Brenster | Joseph | JB |  | 10
3 | Morris | Connor | CM |  | Sprint #2
4 | Kemp | Bobby | BK |  | Priority | Feature ID | Status | Feature | Notes | Branch
5 | Gibbs | Joshua | JG |  | 1 | DTE-PRM-010 | NS | Player Health | Damage only. No healing | DTE-PRM-1012
6 | Calderone | Salvatore | SC |  | 2 | DTE-PRM-011 | NS | Enemy Health | Damage only. No healing | DTE-PRM-1012
7 |  |  |  |  | 3 | DTE-PRM-012 | NS | NPC Health | Damage only. No healing | DTE-PRM-1012
8 |  |  |  |  | 4 | DTE-PRM-013 | NS | Enemy Attack | Melee Attack to player | DTE-PRM-1317
9 |  |  |  |  | 5 | DTE-PRM-014 | NS | Object Class Design | Design class structure for objects | Master
10 |  |  |  |  | 6 | DTE-PRM-015 | NS | Enemy Attack | Ranged Attack to player | DTE-PRM-1317
Team Production Summary |  |  |  |  | 7 | DTE-PRM-016 | NS | Respawn/Checkpoint | Checkpoint first, then respawn | DTE-PRM-1317
Programming team's plan is to have basic character definitions set up before Thanksgiving week. After Thanksgiving week, UI and Environment will be implemented |  |  |  |  | 8 | DTE-PRM-017 | NS | Instant death | Ensure it works with respawn/checkpoint | DTE-PRM-1317
9
10
Sprint #3
[5 empty] | Priority | Feature ID | Status | Feature | Notes | Branch
Production Backlog Burn Table |  |  |  |  | 1
Total |  | 17 | 6 | 11 | 2
Sprint #1 |  |  |  |  | 3
Date Start | 2017NOV10 | Targets | Completed | To Go | 4
Date End | 2017NOV16 | 9 | 6 | 3 | 5
Sprint #2 |  |  |  |  | 6
Date Start | 2017NOV17 | Targets | Completed | To Go | 7
Date End | 2017NOV23 | 8 | 0 | 8 | 8
Sprint #3 |  |  |  |  | 9
Date Start | 2017NOV24 | Targets | Completed | To Go | 10
Date End | 2017NOV30 | 0 | 0 | 0 | Sprint #4
Sprint #4 |  |  |  |  | Priority | Feature ID | Status | Feature | Notes | Branch
Date Start | 2017DEC01 | Targets | Completed | To Go | 1
Date End | 2017DEC07 | 0 | 0 | 0 | 2
3
4
5
6
7
8
9
10

## Sprint #1 Backlog
Sprint #1 Backlog
Sprint Overview
Sprint Start: | 2017NOV10
Sprint End: | 2017NOV16
Demo On: | 2017 NOV 17
Date Table
Day # | Is On | Target Tasks | Target To Go | Comp. Tasks | Tasks To Go
1 | 2017NOV10 | 12 | 8 | 12 | 8
2 | 2017NOV11 | 1 | 7 | 1 | 7
3 | 2017NOV12 | 6 | 1 | 4 | 3
4 | 2017NOV13 | 1 | 0 | 1 | 2
5 | 2017NOV14 | 0 | 0 | 0 | 2
6 | 2017NOV15 | 0 | 0 | 0 | 2
7 | 2017NOV16 | 0 | 0 | 1 | 1
Remember: Baby Steps!
Task Board
Task ID | Feature ID | Started By | Day Projected | NST | INW | TST/RVW | MRG | CMP | Day Finished | Finished By | Task Description
PRM001 | DTE-PRM-001 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Character Class, which will become parent class for others
PRM002 | DTE-PRM-002 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct NPC Class, inherited from Character class
PRM003 | DTE-PRM-003 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Enemy Class, inherited from Character class
PRM004 | DTE-PRM-004 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Player class inherited from Character class
PRM005 | N/A | ALL | 1 | O | X | X | X | O | 1 | ALL | Adjust Class Structures
PRM006 | N/A | SC | 3 | O | O | O |  |  |  |  | Design Single Level for feature testing
PRM007 | DTE-PRM-006 | JB | 3 | O | O | O | O | O | 3 | JB | Player Movement Phase I: Left and right with sprite inversion
PRM008 | DTE-PRM-006 | JB | 3 | O | O | O | O | O | 3 | JB | Player Movement Phase II: Single jump
PRM009 | DTE-PRM-006 | CM | 3 | O | O | O | O | O | 3 | CM | Player Movement Phase III: Camera control
PRM010 | DTE-PRM-007 | BK | 3 | O | O | O | O | O | 3 | BK | Enemy Movement Phase I: Enemy approaching to player
PRM011 | DTE-PRM-007 | BK | 4 | O | O | O | O | O | 7 | BK | Enemy Movement Phase II: Enemy pathfinding (As simple as possible)
PRM012 | DTE-PRM-008 | BK | 3 | O | O | O | O | O | 4 | BK | NPC Movement Phase I: NPC following player
PRM013 | N/A | CS | 2 | O | O | O | O | O | 2 | CS | Create Character Super Class Script
PRM014 | DTE-PRM-009 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Item Super Class
PRM015 | DTE-PRM-009 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Consumable Class, inherited from Item
PRM016 | DTE-PRM-009 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Armour Class, inherited from Equipment
PRM017 | DTE-PRM-009 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct MeleeWeapon Class, inherited from Weapon
PRM018 | DTE-PRM-009 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct RangedWeapon Class, inherited from Weapon
PRM019 | DTE-PRM-009 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Weapon Class, inherited from Equipment
PRM020 | DTE-PRM-009 | ALL | 1 | O | X | X | X | O | 1 | ALL | Construct Equipment Class, inherited from Item

## Sprint #2 Backlog
Sprint #2 Backlog
Sprint Overview
Sprint Start: | 2017NOV17
Sprint End: | 2017NOV23
Demo On: | 2017 NOV 24
Date Table
Day # | Is On | Target Tasks | Target To Go | Comp. Tasks | Tasks To Go
1 | 2017NOV17 | 10 | 20 | 2 | 28
2 | 2017NOV18 | 6 | 14 | 0 | 28
3 | 2017NOV19 | 0 | 14 | 0 | 28
4 | 2017NOV20 | 12 | 2 | 0 | 28
5 | 2017NOV21 | 0 | 2 | 0 | 28
6 | 2017NOV22 | 0 | 2 | 0 | 28
7 | 2017NOV23 | 2 | 0 | 0 | 28
Remember: Baby Steps!
Task Board
Task ID | Feature ID | Started By | Day Projected | NST | INW | TST/RVW | MRG | CMP | Day Finished | Finished By | Task Description
PRM-001 | DTE-PRM-014 | ALL | 1 | O | X | X | X | O | 1 | ALL | Discuss class structure for environmental objects
PRM-002 | DTE-PRM-014 | ALL | 1 | O | X | X | X | O | 1 | ALL | Discuss class structure for game controller
PRM-003 | DTE-PRM-014 | CS | 1 | O | [6 empty] | Create script structure for environmental objects
PRM-004 | DTE-PRM-014 | CS | 1 | O | [6 empty] | Create script for basic game controller
PRM-005 | N/A | CS | 1 | O | [6 empty] | Merge/Stabilize incoming pull requests
PRM-006 | N/A | JG | 4 | O | [6 empty] | Create branch DTE-PRM-1012
PRM-007 | DTE-PRM-010 | JG | 4 | O | [6 empty] | Add script function to player to receive numerical damage
PRM-008 | DTE-PRM-010 | JG | 4 | O | [6 empty] | Add script function to player to take numerical damage to health
PRM-009 | DTE-PRM-011 | JG | 4 | O | [6 empty] | Add script function to enemy to receive numerical damage
PRM-010 | DTE-PRM-011 | JG | 4 | O | [6 empty] | Add script function to enemy to take numerical damage to health
PRM-011 | DTE-PRM-012 | JG | 4 | O | [6 empty] | Add script function to NPC to receive numerical damage
PRM-012 | DTE-PRM-012 | JG | 4 | O | [6 empty] | Add script function to NPC to take numerical damage to health
PRM-013 | N/A | JG | 4 | O | X | X | X |  |  |  | Merge branch DTE-PRM-1012 to Master
PRM-014 | N/A | BK | 2 | O | X | X | X |  |  |  | Create branch DTE-PRM-1317
PRM-015 | DTE-PRM-013 | BK | 2 | O | [6 empty] | Add trigger area for enemy melee attack
PRM-016 | DTE-PRM-013 | BK | 2 | O | [6 empty] | Link enemy attack function to trigger area and perform numerical dmg.
PRM-017 | DTE-PRM-015 | BK | 2 | O | [6 empty] | Add prefab for basic projectile (For ranged attack)
PRM-018 | DTE-PRM-015 | BK | 2 | O | [6 empty] | Add function to enemy script to perform ranged attack
PRM-019 | DTE-PRM-015 | BK | 2 | O | [6 empty] | Link ranged attack to scripts and perform numerical damage
PRM-020 | DTE-PRM-016 | CM | 4 | O | [6 empty] | Create trigger area for checkpoints (Either prefab or hand-made)
PRM-021 | DTE-PRM-016 | CM | 4 | O | [6 empty] | Link trigger area to game controller to save player's chcekpoint
PRM-022 | DTE-PRM-016 | CM | 4 | O | [6 empty] | Link trigger area to player so player can be respawned at saved CP
PRM-023 | DTE-PRM-017 | SC | 1 | O | [6 empty] | Create trigger area for instant death (preferred out of bound for now)
PRM-024 | DTE-PRM-017 | CM | 4 | O | [6 empty] | Link trigger area to player to perform respawn
PRM-025 | DTE-PRM-017 | SC | 1 | O | [6 empty] | Link trigger area to game controller to indicate instant death
PRM-026 | DTE-PRM-017 | SC | 1 | O | [6 empty] | Link trigger area to enemy to instantly destory enemy GO
PRM-027 | DTE-PRM-017 | SC | 1 | O | [6 empty] | Link trigger area to NPC to instantly destory NPC GO
PRM-028 | N/A | SC | 7 | O | X | X | X |  |  |  | Merge branch DTE-PRM-1317 to Master
PRM-029 | N/A | CS | 7 | O | [6 empty] | Merge/Stabilize incoming pull requests
PRM-030 | N/A | SC | 1 | O | [6 empty] | Complete simple level

## Sprint #3 Backlog
Sprint #3 Backlog
Sprint Overview
Sprint Start: | 2017NOV03
Sprint End: | 2017NOV09
Demo On: | TBD
Date Table
Day # | Is On | Target Tasks | Target To Go | Comp. Tasks | Tasks To Go
1 | 2017NOV03 | 1 | 6 | 2 | 5
2 | 2017NOV04 | 1 | 5 | 0 | 5
3 | 2017NOV05 | 1 | 4 | 0 | 5
4 | 2017NOV06 | 1 | 3 | 0 | 5
5 | 2017NOV07 | 1 | 2 | 0 | 5
6 | 2017NOV08 | 1 | 1 | 0 | 5
7 | 2017NOV09 | 1 | 0 | 0 | 5
Remember: Baby Steps!
Task Board
Task ID | Feature ID | Started By | Day Projected | NST | INW | TST/RVW | MRG | CMP | Day Finished | Finished By | Task Description
ABC-### | DTE-ABC-### | INITIALS | 1 | O | O | O | O | O | 1 | INITIALS | Type detailed task description(Not to long, but enough to understand)
ABC-### |  |  | 2 | O | O | O | O | O | 1
ABC-### |  |  | 3 | O | O | O
ABC-### |  |  | 4 | O | O
ABC-### |  |  | 5 | O
ABC-### |  |  | 6 | O
ABC-### |  |  | 7 | O

## Sprint #4 Backlog
Sprint #4 Backlog
Sprint Overview
Sprint Start: | 2017NOV03
Sprint End: | 2017NOV09
Demo On: | TBD
Date Table
Day # | Is On | Target Tasks | Target To Go | Comp. Tasks | Tasks To Go
1 | 2017NOV03 | 1 | 6 | 2 | 5
2 | 2017NOV04 | 1 | 5 | 0 | 5
3 | 2017NOV05 | 1 | 4 | 0 | 5
4 | 2017NOV06 | 1 | 3 | 0 | 5
5 | 2017NOV07 | 1 | 2 | 0 | 5
6 | 2017NOV08 | 1 | 1 | 0 | 5
7 | 2017NOV09 | 1 | 0 | 0 | 5
Remember: Baby Steps!
Task Board
Task ID | Feature ID | Started By | Day Projected | NST | INW | TST/RVW | MRG | CMP | Day Finished | Finished By | Task Description
ABC-### | DTE-ABC-### | INITIALS | 1 | O | O | O | O | O | 1 | INITIALS | Type detailed task description(Not to long, but enough to understand)
ABC-### |  |  | 2 | O | O | O | O | O | 1
ABC-### |  |  | 3 | O | O | O
ABC-### |  |  | 4 | O | O
ABC-### |  |  | 5 | O
ABC-### |  |  | 6 | O
ABC-### |  |  | 7 | O